## plan
project_id | activity_id | phase | phase_order | activity_sequence | activity_name | planned_duration_days | criticality | status | expected_equipment
P00001 | P00001_A0001 | Preconstruction | 1 | 1 | Design Finalisation | 26 | 0.6854 | Planned | ['worker']
P00001 | P00001_A0002 | Preconstruction | 1 | 2 | Procurement Planning | 20 | 0.7652 | Planned | ['worker']
P00001 | P00001_A0003 | Preconstruction | 1 | 3 | Design Finalisation | 29 | 0.3375 | Planned | ['worker']
P00001 | P00001_A0004 | Preconstruction | 1 | 4 | Design Finalisation | 25 | 0.5346 | Planned | ['worker']
P00001 | P00001_A0005 | Site Preparation | 2 | 5 | Site Clearance | 13 | 0.5794 | Planned | ['worker', 'bulldozer', 'excavator', 'loader', 'truck']
P00001 | P00001_A0006 | Site Preparation | 2 | 6 | Temporary Facilities | 9 | 0.8696 | Planned | ['worker', 'truck', 'other_vehicle']
P00001 | P00001_A0007 | Site Preparation | 2 | 7 | Site Clearance | 7 | 0.5094 | Planned | ['worker', 'bulldozer', 'excavator', 'loader', 'truck']
P00001 | P00001_A0008 | Site Preparation | 2 | 8 | Survey and Setting Out | 4 | 0.7722 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0009 | Site Preparation | 2 | 9 | Site Clearance | 13 | 0.8326 | Planned | ['worker', 'bulldozer', 'excavator', 'loader', 'truck']
P00001 | P00001_A0010 | Earthwork | 3 | 10 | Dewatering | 19 | 0.508 | Planned | ['worker', 'excavator', 'truck', 'other_vehicle']
P00001 | P00001_A0011 | Earthwork | 3 | 11 | Dewatering | 14 | 0.1134 | Planned | ['worker', 'excavator', 'truck', 'other_vehicle']
P00001 | P00001_A0012 | Earthwork | 3 | 12 | Soil Disposal | 20 | 0.4175 | Planned | ['worker', 'excavator', 'loader', 'truck']
P00001 | P00001_A0013 | Earthwork | 3 | 13 | Compaction | 12 | 0.7057 | Planned | ['worker', 'roller', 'loader', 'truck']
P00001 | P00001_A0014 | Earthwork | 3 | 14 | Backfilling | 12 | 0.7199 | Planned | ['worker', 'excavator', 'loader', 'truck']
P00001 | P00001_A0015 | Earthwork | 3 | 15 | Soil Disposal | 17 | 0.3703 | Planned | ['worker', 'excavator', 'loader', 'truck']
P00001 | P00001_A0016 | Earthwork | 3 | 16 | Backfilling | 12 | 0.6639 | Planned | ['worker', 'excavator', 'loader', 'truck']
P00001 | P00001_A0017 | Earthwork | 3 | 17 | Excavation | 17 | 0.3016 | Planned | ['worker', 'excavator', 'loader', 'truck']
P00001 | P00001_A0018 | Earthwork | 3 | 18 | Backfilling | 19 | 0.6151 | Planned | ['worker', 'excavator', 'loader', 'truck']
P00001 | P00001_A0019 | Foundation | 4 | 19 | Footing Concrete | 10 | 0.559 | Planned | ['worker', 'concrete_mixer', 'pump_truck', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0020 | Foundation | 4 | 20 | Footing Reinforcement | 13 | 0.4674 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'vehicle_crane']
P00001 | P00001_A0021 | Foundation | 4 | 21 | PCC | 9 | 0.8812 | Planned | ['worker', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0022 | Foundation | 4 | 22 | Footing Reinforcement | 11 | 0.3879 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'vehicle_crane']
P00001 | P00001_A0023 | Foundation | 4 | 23 | PCC | 10 | 0.5623 | Planned | ['worker', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0024 | Foundation | 4 | 24 | Footing Formwork | 12 | 0.9026 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'vehicle_crane']
P00001 | P00001_A0025 | Foundation | 4 | 25 | Footing Reinforcement | 17 | 0.8751 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'vehicle_crane']
P00001 | P00001_A0026 | Foundation | 4 | 26 | Footing Concrete | 9 | 0.4154 | Planned | ['worker', 'concrete_mixer', 'pump_truck', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0027 | Foundation | 4 | 27 | Footing Concrete | 5 | 0.7064 | Planned | ['worker', 'concrete_mixer', 'pump_truck', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0028 | Foundation | 4 | 28 | PCC | 5 | 0.5959 | Planned | ['worker', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0029 | Foundation | 4 | 29 | PCC | 9 | 0.3752 | Planned | ['worker', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0030 | Foundation | 4 | 30 | Footing Reinforcement | 8 | 0.9242 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'vehicle_crane']
P00001 | P00001_A0031 | Foundation | 4 | 31 | Footing Reinforcement | 20 | 0.7786 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'vehicle_crane']
P00001 | P00001_A0032 | Structural Frame | 5 | 32 | Slab Reinforcement | 12 | 0.4729 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0033 | Structural Frame | 5 | 33 | Column Reinforcement | 14 | 0.7589 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0034 | Structural Frame | 5 | 34 | Beam Concrete | 5 | 0.766 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0035 | Structural Frame | 5 | 35 | Beam Formwork | 17 | 0.5688 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0036 | Structural Frame | 5 | 36 | Column Formwork | 19 | 0.9263 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0037 | Structural Frame | 5 | 37 | Beam Formwork | 11 | 0.3095 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0038 | Structural Frame | 5 | 38 | Beam Reinforcement | 21 | 0.6776 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0039 | Structural Frame | 5 | 39 | Column Concrete | 8 | 0.8284 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0040 | Structural Frame | 5 | 40 | Slab Formwork | 21 | 0.5246 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0041 | Structural Frame | 5 | 41 | Slab Reinforcement | 24 | 0.6743 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0042 | Structural Frame | 5 | 42 | Slab Reinforcement | 22 | 0.5278 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0043 | Structural Frame | 5 | 43 | Slab Formwork | 10 | 0.7669 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0044 | Structural Frame | 5 | 44 | Slab Reinforcement | 18 | 0.3922 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0045 | Structural Frame | 5 | 45 | Column Formwork | 22 | 0.5552 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0046 | Structural Frame | 5 | 46 | Beam Formwork | 8 | 0.3217 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0047 | Structural Frame | 5 | 47 | Slab Formwork | 10 | 0.9129 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0048 | Structural Frame | 5 | 48 | Column Formwork | 14 | 0.479 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0049 | Structural Frame | 5 | 49 | Curing | 11 | 0.7383 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0050 | Structural Frame | 5 | 50 | Slab Formwork | 11 | 0.6366 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0051 | Structural Frame | 5 | 51 | Column Concrete | 10 | 0.2572 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0052 | Structural Frame | 5 | 52 | Column Formwork | 21 | 0.5016 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0053 | Structural Frame | 5 | 53 | Beam Reinforcement | 10 | 0.805 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0054 | Structural Frame | 5 | 54 | Slab Concrete | 9 | 0.084 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0055 | Structural Frame | 5 | 55 | Slab Concrete | 7 | 0.6917 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0056 | Structural Frame | 5 | 56 | Column Formwork | 13 | 0.7213 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0057 | Structural Frame | 5 | 57 | Column Formwork | 20 | 0.1829 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0058 | Structural Frame | 5 | 58 | Column Concrete | 12 | 0.7062 | Planned | ['worker', 'tower_crane', 'hanging_hook', 'concrete_mixer', 'pump_truck']
P00001 | P00001_A0059 | Masonry | 6 | 59 | Blockwork | 22 | 0.806 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0060 | Masonry | 6 | 60 | Internal Brickwork | 16 | 0.6308 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0061 | Masonry | 6 | 61 | Blockwork | 25 | 0.93 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0062 | Masonry | 6 | 62 | Internal Brickwork | 12 | 0.4279 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0063 | Masonry | 6 | 63 | Internal Brickwork | 26 | 0.5925 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0064 | Masonry | 6 | 64 | External Brickwork | 10 | 0.6757 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0065 | Masonry | 6 | 65 | External Brickwork | 19 | 0.8867 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0066 | Masonry | 6 | 66 | Internal Brickwork | 10 | 0.6611 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0067 | Masonry | 6 | 67 | Blockwork | 12 | 0.4975 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0068 | Masonry | 6 | 68 | Internal Brickwork | 27 | 0.8108 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0069 | Masonry | 6 | 69 | Internal Brickwork | 13 | 0.1362 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0070 | Masonry | 6 | 70 | External Brickwork | 19 | 0.6197 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0071 | Masonry | 6 | 71 | Blockwork | 13 | 0.6101 | Planned | ['worker', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0072 | MEP | 7 | 72 | Electrical Final Installation | 10 | 0.7748 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0073 | MEP | 7 | 73 | Electrical Final Installation | 10 | 0.261 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0074 | MEP | 7 | 74 | Plumbing Rough-in | 20 | 0.1921 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0075 | MEP | 7 | 75 | Electrical Final Installation | 23 | 0.7006 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0076 | MEP | 7 | 76 | Fire Protection | 19 | 0.7054 | Planned | ['worker', 'vehicle_crane', 'other_vehicle']
P00001 | P00001_A0077 | MEP | 7 | 77 | Fire Protection | 8 | 0.8306 | Planned | ['worker', 'vehicle_crane', 'other_vehicle']
P00001 | P00001_A0078 | MEP | 7 | 78 | HVAC Installation | 23 | 0.2327 | Planned | ['worker', 'vehicle_crane', 'tower_crane', 'hanging_hook']
P00001 | P00001_A0079 | MEP | 7 | 79 | Electrical Final Installation | 16 | 0.3967 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0080 | MEP | 7 | 80 | Plumbing Rough-in | 30 | 0.1833 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0081 | MEP | 7 | 81 | Plumbing Rough-in | 23 | 0.9384 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0082 | MEP | 7 | 82 | Plumbing Rough-in | 16 | 0.3453 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0083 | MEP | 7 | 83 | Plumbing Rough-in | 20 | 0.4593 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0084 | MEP | 7 | 84 | Electrical Final Installation | 10 | 0.3891 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0085 | Finishing | 8 | 85 | Internal Plastering | 19 | 0.6675 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0086 | Finishing | 8 | 86 | Doors and Windows | 16 | 0.7512 | Planned | ['worker', 'vehicle_crane', 'hanging_hook']
P00001 | P00001_A0087 | Finishing | 8 | 87 | External Plastering | 10 | 0.6286 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0088 | Finishing | 8 | 88 | Flooring | 26 | 0.3302 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0089 | Finishing | 8 | 89 | Painting | 27 | 0.4383 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0090 | Finishing | 8 | 90 | Internal Plastering | 27 | 0.5869 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0091 | Finishing | 8 | 91 | Painting | 8 | 0.6169 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0092 | Finishing | 8 | 92 | Doors and Windows | 9 | 0.7052 | Planned | ['worker', 'vehicle_crane', 'hanging_hook']
P00001 | P00001_A0093 | Finishing | 8 | 93 | Flooring | 21 | 0.5757 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0094 | Finishing | 8 | 94 | Flooring | 9 | 0.6866 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0095 | Finishing | 8 | 95 | External Plastering | 23 | 0.9251 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0096 | Finishing | 8 | 96 | External Plastering | 30 | 0.6423 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0097 | Finishing | 8 | 97 | False Ceiling | 19 | 0.9532 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0098 | Finishing | 8 | 98 | Internal Plastering | 17 | 0.6069 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0099 | Finishing | 8 | 99 | Doors and Windows | 20 | 0.4744 | Planned | ['worker', 'vehicle_crane', 'hanging_hook']
P00001 | P00001_A0100 | Finishing | 8 | 100 | Doors and Windows | 11 | 0.188 | Planned | ['worker', 'vehicle_crane', 'hanging_hook']
P00001 | P00001_A0101 | External Works | 9 | 101 | Landscaping | 15 | 0.1792 | Planned | ['worker', 'excavator', 'loader', 'truck', 'other_vehicle']
P00001 | P00001_A0102 | External Works | 9 | 102 | Drainage | 14 | 0.3853 | Planned | ['worker', 'excavator', 'loader', 'truck']
P00001 | P00001_A0103 | External Works | 9 | 103 | Road Works | 26 | 0.3962 | Planned | ['worker', 'bulldozer', 'roller', 'loader', 'truck']
P00001 | P00001_A0104 | External Works | 9 | 104 | Road Works | 25 | 0.4877 | Planned | ['worker', 'bulldozer', 'roller', 'loader', 'truck']
P00001 | P00001_A0105 | Commissioning | 10 | 105 | Final Commissioning | 9 | 0.6849 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0106 | Commissioning | 10 | 106 | Inspection | 8 | 0.3939 | Planned | ['worker', 'other_vehicle']
P00001 | P00001_A0107 | Commissioning | 10 | 107 | Defect Rectification | 17 | 0.7643 | Planned | ['worker', 'other_vehicle']

## equipment_descriptions
equipment_class | description
worker | Construction workers and site personnel performing manual, supervisory, installation, finishing, and inspection tasks.
tower_crane | Fixed tower crane used to lift and position heavy materials such as reinforcement, formwork, masonry materials, and structural elements.
hanging_hook | Suspended crane hook/load attachment visible below a lifting crane, used for material lifting and positioning.
vehicle_crane | Mobile truck-mounted or all-terrain crane used for lifting materials and equipment at different locations on the construction site.
roller | Road roller/compactor used to compact soil, aggregate, sub-base, and road construction layers.
bulldozer | Tracked earthmoving machine with a front blade used for clearing, pushing, spreading, and rough grading soil and materials.
excavator | Hydraulic excavator used for digging, trenching, loading, site clearance, and other earthmoving operations.
truck | Site or tipper truck used to transport soil, construction materials, debris, and other loads around or away from the site.
loader | Wheel loader used to load, move, and stockpile soil, aggregate, debris, and construction materials.
pump_truck | Concrete pump truck used to transfer and place ready-mix concrete through a boom or pumping system.
concrete_mixer | Concrete mixer/ready-mix vehicle used to transport and continuously mix concrete before placement.
pile_driver | Pile-driving machine used to install foundation piles into the ground.
other_vehicle | Other construction-related vehicle or mobile equipment not covered by the defined equipment classes.